Implementation Matrix

MOU to Framework Mapping

The Operational Bridge Between Political Commitments and Technical Protocols

Version 1.0  |  June 2026  |  Confidential — Authorized Negotiators Only

# Table of Contents

Right-click the TOC and select "Update Field" to refresh page numbers

Part 1: Executive Summary	3

Part 2: MOU-to-Framework Cross-Reference Matrix	4

Part 3: Annex-to-MOU Cross-Reference	10

Part 4: Consolidated Timeline (Day 1 to Day 730)	13

Part 5: Crisis Response Matrix	16

Part 6: Key Contacts Directory	19

Part 7: Implementation Checklist	20

# Part 1: Executive Summary

## The Core Trade

This Implementation Matrix bridges the political 14-article Memorandum of Understanding (MOU) between the United States and the Islamic Republic of Iran with the technical implementation frameworks that operationalize each commitment. It provides a single operational reference for negotiators, implementers, crisis managers, and senior officials.

## Total Duration

The primary implementation window is 60 days from MOU signature (Article 3), extendable by mutual consent. Phase I stabilization extends to 365 days under the Provisional Steps Framework v1.8 (Article 17, Rolling Horizon Architecture). Day 180 marks the disposition pathway default trigger; Day 730 marks the Pathway W (Agriculture and Food Security) irreversible default.

## Five Critical Milestones

- Day 1: Ceasefire enters force on all fronts; HEU stockpile placed under IAEA dual-lock custody; $5B mutual escrow deposit placed; oil/petrochemical waivers issued (MOU Articles 1, 4, 5, 10)

- Day 7: Synchronized blockade lift; Hormuz mine-free with 72-hour transit; first escrow tranche ($2.5B) releases (MOU Articles 4, 5; PSF Article 6; Annex Mi)

- Day 14: IAEA baseline inventory complete; dual-key custody fully established (PSF Article 1.1; Annex Y)

- Day 30: Hormuz at pre-war transit volume; first sanctions relief tranche; 15% frozen asset release ($3.6B) (MOU Articles 5, 7, 11; Annex S)

- Day 60: Final agreement deadline; full structural relief conversion or Phase II deadlock procedure (MOU Article 3; Annex D)

## Bottom Line

The core trade: Iran neutralizes its weapons-usable uranium under verified IAEA custody and reopens the Strait of Hormuz; the United States lifts the naval blockade and releases frozen assets in verified, reversible tranches. No cash moves on Day 1. Either side retains an orderly exit ramp. The $300B rehabilitation fund (MOU Article 6) remains a political aspiration requiring a separate Phase III negotiation track — it is not operationalized in any existing framework.

# Part 2: MOU-to-Framework Cross-Reference Matrix

The following matrix maps each of the 14 MOU articles to its primary implementing framework, specific provisions, operational triggers, responsible parties, timelines, verification methods, and key differences from the political commitment.

## MOU Article 1: Immediate End to War on All Fronts

| Field | Mapping |
| --- | --- |
| Primary Framework | MOU of PEACE v7.0 (Article 6 - Regional and Ceasefire Core) + PSF v1.8 Appendix E (Lebanon Protocol) + Hormuz Synchronization Compact v7.3 (Article XI: Lebanon Firewall Protocol) |
| Specific Provisions | MOU of PEACE Art. 6.1 (Rolling Ceasefire); Art. 6.2 (Territorial Freeze-in-Place); PSF Appendix E (Lebanon Escalation Ladder); HSC Annex K (Lebanon Firewall and Stabilization Protocol, Sections 1-3) |
| Operational Trigger | MOU signature; ceasefire enters force immediately across all fronts including Lebanon, Gaza, Syria, and Yemen |
| Responsible Party | US + Iran + Allies; PCC oversight; guarantor states (Pakistan, Oman, China, Russia, EU/E3+, Qatar) |
| Timeline | Immediate on signature; 60-day initial period, auto-renewing for successive 30-day periods unless written non-renewal notice given 15 days before expiry |
| Verification Method | Regional Stabilization Rounds on fixed calendar; PCC monitoring; Shared Digital Registry (Annex U); independent satellite verification |
| Key Difference | MOU says "immediate and permanent"; frameworks add modularity — breach on one front does not automatically breach nuclear/maritime cores (Firewall Architecture) |

## MOU Article 2: Sovereignty and Territorial Integrity

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Preamble — No Regime Change Objective + Domestic Framing Autonomy) + MOU of PEACE v7.0 (Article 1.7) |
| Specific Provisions | PSF Preamble (No Regime Clause, operative and binding); PSF Article 16.4 (Syria Freedom of Action); MOU of PEACE Art. 1.7 (Framing Autonomy); Annex IC (Institutional Continuity) |
| Operational Trigger | Continuous — applies throughout Framework duration |
| Responsible Party | Both Parties; enforced by PCC; binding PCA arbitration available |
| Timeline | Ongoing throughout Framework and 5-year post-termination survival period |
| Verification Method | Non-interference monitored via guarantor state reporting; violations arbitrable at PCA |
| Key Difference | MOU states general principle; frameworks add explicit prohibition on using Framework access for intelligence, regime change, or internal political disruption (PSF Preamble, operative and binding) |

## MOU Article 3: Final Agreement Within 60 Days

| Field | Mapping |
| --- | --- |
| Primary Framework | MOU of PEACE v7.0 (Article 11 — Phase Transitions) + PSF v1.8 (Article 11 — Letter of Intent) + Annex D (Phase II Deadlock Mechanism) |
| Specific Provisions | MOU of PEACE Art. 11.2 (Phase II entry); PSF Art. 11 (30-Day Letter of Intent); Annex D (Cooling-off → Ministerial Consultation → PCA Arbitration → Extended Phase I fallback) |
| Operational Trigger | Day 60: If no final agreement reached, deadlock procedures activate automatically |
| Responsible Party | All Parties; PCC facilitates; Guarantor Matrix mediates; PCA arbitrates if needed |
| Timeline | Day 60: Deadline or extension by mutual consent; Days 60-150: Deadlock resolution procedures |
| Verification Method | PCC issues Phase II Transition Certificate (MOU of PEACE) or Deadlock Confirmation Certificate (Annex D) |
| Key Difference | MOU says "60 days, extendable"; frameworks operationalize the extension through a 90-day cooling-off period, ministerial consultation, binding PCA arbitration, and automatic reversion to extended Phase I if deadlock persists |

## MOU Article 4: Lift Naval Blockade; 30-Day Restoration

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Article 6 — Synchronized Dual-Blockade Lift) + MOU of PEACE v7.0 (Article 4 — Maritime Stabilization) + HSC v7.3 (Article IV) |
| Specific Provisions | PSF Art. 6.3 (Conditional Review-Based Trigger); MOU of PEACE Art. 4.3 (Synchronized Blockade Lift); Annex Mi (Maritime Implementation Schedule); Annex N (Non-Interdiction Protocol); Annex N.a (Backdoor Closure) |
| Operational Trigger | Day 7: Joint Review Board certifies milestones; both capitals confirm through defense ministers; synchronized lift executes |
| Responsible Party | US 5th Fleet + IRGC Navy + Oman (Maritime Stability Board) |
| Timeline | Day 7: Blockade lift + first commercial transits; Day 30: Pre-war volume restored |
| Verification Method | Lloyd's List + JHA MCC telemetry (Annex W) + Omani naval observers + PSF Article 4.7 (IRGC-Navy Direct Hotline) |
| Key Difference | MOU says "immediately" + "30-day restoration"; frameworks add a conditional Day-7 synchronized lift with human confirmation (not automatic), verification gates, and 24-hour telemetry standard |

## MOU Article 5: Iran Reopens Hormuz; Mine Clearance

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Article 4 — JHTA; Article 5 — MMMF) + MOU of PEACE v7.0 (Article 4.3) + HSC v7.3 (Article IV, Section 4.2) |
| Specific Provisions | PSF Art. 4 (Joint Hormuz Transit Authority); Art. 5 (Multilateral Maritime Maintenance Fund); Annex Mi (Maritime Implementation — Phase 1-3); Annex W (Maritime Telemetry) |
| Operational Trigger | Day 1: Iran begins mine clearance; Day 3: First humanitarian vessel transits; Day 7: Full commercial opening |
| Responsible Party | Iran (mine clearance) + Oman (facilitation) + JHA MCC (coordination) + US 5th Fleet (stand-off posture) |
| Timeline | Day 3: First transit; Day 7: Full opening; Day 30: Pre-war volume; 12-month JHTA pilot phase |
| Verification Method | JHA MCC telemetry (Annex W); IMCA Maritime Operations Center 24/7 channel; PSF Art. 4.7 hotline daily testing at 06:00 UTC |
| Key Difference | MOU says "immediately" + "30 days"; frameworks add a phased reopening (Day 3/7/30), JHTA advisory governance with PGSA sovereignty recalibration, and zero-tolls guarantee |

## MOU Article 6: $300B Rehabilitation Fund

| Field | Mapping |
| --- | --- |
| Primary Framework | NO EXISTING FRAMEWORK OPERATIONALIZES THIS COMMITMENT |
| Specific Provisions | GAP IDENTIFIED — No annex, article, or provision in any framework creates, administers, or governs a $300B fund |
| Operational Trigger | Not operationalized — requires Phase III negotiation track |
| Responsible Party | Not designated — recommend PCC + International Financial Institutions (World Bank, IMF, DFC) |
| Timeline | Not operationalized — recommend 60-day negotiation track post-Day 60 agreement |
| Verification Method | None — not yet operational |
| Key Difference | MOU states "at least $300 billion" as a political aspiration; frameworks provide: $5B mutual escrow (MOU of PEACE), $1B Joint Disposition Fund (PSF), $5B/yr DFC matching (PSF Art. 10), $50M Political Discretion Fund (PSF Art. 7.5). These are operational but far below $300B. |

GAP RECOMMENDATION: Establish a Phase III Negotiation Track for the $300B Rehabilitation Fund, with contributions from the US, Gulf states (Saudi Arabia, UAE, Qatar), EU, and international financial institutions (World Bank, IMF, AIIB). Modeled on the Iraq Reconstruction Fund (2003) and JCPOA economic arrangements.

## MOU Article 7: End All Sanctions

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Article 7 — Graduated Sanctions Relief) + MOU of PEACE v7.0 (Article 5 — Economic Normalization) + HSC v7.3 (Annex L: Sanctions and Financial Architecture) |
| Specific Provisions | PSF Art. 7.1 (30-Day Stabilization Blocks); MOU of PEACE Art. 5.2-5.3 (Frozen-Asset Schedule); Annex S (60-Day Reciprocal Sequencing Schedule); Annex T (Step-Back/Earn-Back Compliance); HSC Annex L.2 (Relief Sequencing Map) |
| Operational Trigger | Day 1: OFAC general license for humanitarian trade; Day 30: First sanctions relief tranche on IAEA certification; Day 45: SWIFT Phase 1; phased thereafter |
| Responsible Party | US Treasury + OFAC + Swiss Escrow Facilitator + PCC |
| Timeline | Day 1: Humanitarian OFAC license; Day 7: $2.5B escrow release; Day 30: First tranche 15%; Day 45: 5-bank SWIFT; Day 60: 30% cumulative; Day 180: 45%; Day 360: 65%; Month 24: 100% |
| Verification Method | IAEA certification gates each tranche; Dashboard tracking; SWIFT MT messaging verification; escrow confirmations |
| Key Difference | MOU says "end all sanctions"; frameworks add graduated, reversible relief tied to verified compliance — not blanket immediate lifting. Targeted Bank Isolation replaces blanket sectoral rollbacks. |

## MOU Article 8: No Nuclear Weapons; Defer Enriched Material

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Article 1 — HEU Custody) + MOU of PEACE v7.0 (Article 3 — Nuclear Stabilization Core) + HSC v7.3 (Article IV, Section 4.2) |
| Specific Provisions | PSF Art. 1.1 (14-day HEU Consolidation); Art. 1.5 (Eleven Disposition Pathways); Art. 1.6 (Day 180 In-Iran Default); MOU of PEACE Art. 3.2 (Disposition of Stockpile); Annex Y (Dual-Key Custody); Annex Z (Transformation Pathways); Annex Ya (Irreversible Disposition Module) |
| Operational Trigger | Day 1: HEU freeze declared; Day 14: Dual-lock custody established; Day 180: Pathway A auto-activates if no pathway selected; Day 730: Pathway W auto-activates |
| Responsible Party | Iran (AEOI) + IAEA + US Technical Agent (dual-key) + Swiss Escrow Facilitator |
| Timeline | Day 1-14: Consolidation; Day 14: Dual-lock active; Day 180: Default Pathway A; Day 365: Iran may request custody termination; Day 730: Pathway W default |
| Verification Method | IAEA dual-lock custody + 24-hour batch telemetry (Annex W) + mass spectrometry + tamper-evident seals + Swiss Dashboard |
| Key Difference | MOU defers nuclear details to final agreement; frameworks provide complete operational architecture: 14-day consolidation, 11 pathways, Day 180/730 defaults, $1B Joint Disposition Fund incentive, Iran unilateral selection right on in-Iran pathways, no US veto on pathways N, O, T, W |

## MOU Article 9: Status Quo Pending Final Agreement

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Article 3 — Mothball Protocol) + MOU of PEACE v7.0 (Article 3.1) + Annex IC (Institutional Continuity) |
| Specific Provisions | PSF Art. 3 (Underground Site Conversion); Art. 2.3 (Centrifuge Production Ban); MOU of PEACE Art. 3.1 (3.67% enrichment cap); Art. 3.7 (Centrifuge Production Ban); Annex IC (State-to-State Obligation); Annex PC (Political Stability Hold) |
| Operational Trigger | Continuous from Day 1: Enrichment cap at 3.67%; no new centrifuge manufacturing; mothball protocol activates |
| Responsible Party | Iran (AEOI) for compliance; IAEA for verification; PCC for oversight |
| Timeline | Day 1: Cap enters force; continuous monitoring; quarterly inspections; 24-hour telemetry standard |
| Verification Method | OLEM continuous monitoring; IAEA quarterly inspections; Black-Box Sensor telemetry (Art. 3.4); air-gapped batch verification (Art. 3.3); 24-hour standard for breakout-relevant facilities |
| Key Difference | MOU says "maintain status quo"; frameworks add specific, measurable constraints: 3.67% hard cap, centrifuge production ban (Tier 2 if violated), automated 48-hour suspension for monitoring failure (Art. 3.6), sliding-scale 12-15 year moratorium |

## MOU Article 10: Oil/Petrochemical Export Waivers

| Field | Mapping |
| --- | --- |
| Primary Framework | MOU of PEACE v7.0 (Article 5.2 — Oil Export Normalization) + PSF v1.8 (Article 1.4 — Synchronized US Commitment) |
| Specific Provisions | MOU of PEACE Art. 5.2 (Track 3: Oil-export normalization up to 2.1 mbpd); Art. 5.7 (Energy and Agricultural Release Valve); PSF Art. 1.4 (Item 2: OFAC general license); PRDD channel |
| Operational Trigger | Day 1: OFAC general license issued; permits issued to whitelisted purchasers; IAEA quarterly pre-clearance |
| Responsible Party | US Treasury (OFAC) + whitelisted purchasers + Central Bank of Iran (PRDD) |
| Timeline | Day 1: Permits issued; Day 30: Full volume normalization; ongoing quarterly IAEA pre-clearance |
| Verification Method | PRDD (Petroleum Revenue Direct Deposit) Swiss-escrow channel; IAEA quarterly pre-clearance; Dashboard tracking |
| Key Difference | MOU says "immediately" + "until lifting of sanctions"; frameworks add PRDD escrow channel (revenue flows through Swiss escrow, not direct), quarterly IAEA pre-clearance, and whitelisted purchaser system |

## MOU Article 11: Release Frozen Assets

| Field | Mapping |
| --- | --- |
| Primary Framework | PSF v1.8 (Article 8 — Neutral Escrow) + MOU of PEACE v7.0 (Article 5.2-5.3) + HSC v7.3 (Annex C: Frozen Asset Release Schedule) |
| Specific Provisions | PSF Art. 8 (Neutral Escrow and Asset Shielding); MOU of PEACE Art. 5.3 (Frozen-Asset Schedule); Art. 5.4 (Reversibility + Humanitarian Firewall); HSC Annex C (Two-Tranche Structure + Safeguards) |
| Operational Trigger | Day 1: $5B mutual escrow deposited; Day 7: $2.5B releases if Hormuz mine-free; Day 15: $2.5B on continued compliance; Day 30: First frozen-asset tranche (15% / ~$3.6B) |
| Responsible Party | Swiss Escrow Facilitator (Zurich) + Omani Escrow (Muscat) + US Treasury + Central Bank of Iran |
| Timeline | Day 7: $2.5B; Day 15: $2.5B; Day 30: 15% ($3.6B); Day 60: 30% cumulative; Day 180: 45%; Day 360: 65%; Month 24: 100% |
| Verification Method | Escrow confirmations via Swiss Dashboard; IAEA certification gates each tranche; SOFR + CPI interest accrual verification |
| Key Difference | MOU says "released and made fully available"; frameworks add: staged reversible releases (not lump sum), escrow protection (not direct transfer), interest accrual at SOFR + inflation, humanitarian firewall (one-way protection), step-back/earn-back governance |

## MOU Article 12: Implementation Mechanism

| Field | Mapping |
| --- | --- |
| Primary Framework | MOU of PEACE v7.0 (Article 9 — Governance) + PSF v1.8 (Article 25 — Joint Coordination Council) + HSC v7.3 (Article VIII) |
| Specific Provisions | MOU of PEACE Art. 9 (PCC — Political & Compliance Council); PSF Art. 25 (JCC); Art. 26 (Political Consultation Channel); Annex Mo (Joint Monitoring Cell Charter); HSC Art. VIII (Neutral Guarantor and Governance) |
| Operational Trigger | Day 1: All governance bodies stand up; crisis contacts designated and tested |
| Responsible Party | PCC Co-Chairs (US + Iran); JMC Convenor (rotating US/Iran 90-day); JMC Deputy (Pakistan); Swiss Facilitator; Guarantor Matrix |
| Timeline | Day 1: Operational; quarterly PCC meetings; monthly contact tests at 06:00 UTC; emergency sessions within 4-24 hours |
| Verification Method | Dashboard governance tracking; Swiss-hosted transparency; annual Human-in-the-Loop Audit (PSF Art. 27) |
| Key Difference | MOU says "implementation mechanism will be established"; frameworks specify: PCC (3 bodies only, by design), JMC with rotating convenor, 48-hour emergency session capability, consensus-minus-one voting, annual AI audit |

## MOU Article 13: Negotiate Remaining Articles

| Field | Mapping |
| --- | --- |
| Primary Framework | MOU of PEACE v7.0 (Article 11 — Phase Transitions) + PSF v1.8 (Article 17 — Rolling Horizon) |
| Specific Provisions | MOU of PEACE Art. 11 (Phase II entry after Phase I verification); Art. 13 (Regional and Israel Coordination); PSF Art. 17 (Rolling Horizon — 180-day conditional auto-renewal); Appendix D (Rolling Executive Option) |
| Operational Trigger | Upon receipt of assurances on Articles 4, 5, 10, 11 implementation; continued implementation confirmed |
| Responsible Party | All Parties; PCC manages transition; ministerial-level engagement for Phase II |
| Timeline | Days 30-60: Phase II preparation; Day 60: Phase II entry or deadlock procedures |
| Verification Method | PCC Phase II Transition Certificate (requires 75% sustained compliance score, no single stripe below 60%) |
| Key Difference | MOU says "negotiate remaining articles"; frameworks add: explicit Phase II entry criteria (75% compliance threshold), rolling horizon architecture (180-day active confirmation required), and deadlock fallback (Annex D) if transition fails |

## MOU Article 14: UN Security Council Resolution

| Field | Mapping |
| --- | --- |
| Primary Framework | NOT ADDRESSED IN ANY FRAMEWORK — GAP IDENTIFIED |
| Specific Provisions | No framework contains provisions for UNSC resolution drafting, sponsorship, or adoption. Annex IC (Institutional Continuity) references UNSC in passing but does not operationalize Article 14. |
| Operational Trigger | Not operationalized — requires standalone diplomatic track |
| Responsible Party | Not designated — recommend joint US-Iran diplomatic mission to UNSC P5 members |
| Timeline | Not operationalized — recommend parallel track beginning Day 1 |
| Verification Method | None — not yet operational |
| Key Difference | MOU requires binding UNSC resolution; frameworks are silent on UNSC. This reflects the political reality that UNSC action requires P5 consensus (including Russian and Chinese support), which cannot be guaranteed through technical frameworks. |

GAP RECOMMENDATION: Establish a dedicated UNSC Track led by a joint US-Iran diplomatic team (supported by Oman and Pakistan as facilitators) to draft and sponsor a binding Chapter VII resolution. Begin informal P5 consultations on Day 1. Target adoption by Day 90. Model on UNSCR 2231 (2015) for the JCPOA.

# Part 3: Annex-to-MOU Cross-Reference

This reverse-index maps each major annex back to the MOU articles it serves, with a summary of its key function. Annexes are listed alphabetically.

| Annex | Implements MOU Article(s) | Key Function |
| --- | --- | --- |
| Annex IC (Institutional Continuity) | Articles 2, 9 | State-to-state obligation survival: survives regime change or election, remains binding on successor governments for 5 years post-termination |
| Annex K (Lebanon Firewall) | Articles 1, 12 | Differential Band processing for Lebanon: firewall architecture prevents Lebanon incidents from breaching nuclear/maritime cores; cascading barriers; compliance credits |
| Annex L (Sanctions & Financial Architecture) | Articles 7, 10 | Sanctions inventory framework; relief sequencing map; tranche activation logic; banking compliance architecture; escrow architecture |
| Annex Mi (Maritime Implementation) | Articles 4, 5 | Mine clearance schedule; phased Hormuz reopening (Day 3/7/30); transit corridor definition; Joint Maritime Coordination Cell protocols |
| Annex Mo (Joint Monitoring Cell Charter) | Article 12 | JMC governance: rotating convenor (US/Iran 90-day), Deputy (Pakistan); body-of-three structure; dispute resolution; unanimity rule |
| Annex N (Non-Interdiction) | Articles 4, 5 | Zero-tolls guarantee; no boarding; no delays for non-sanctioned vessels; inspection protocols |
| Annex N.a (Backdoor Closure) | Articles 4, 5 | Automatic $1M/day penalty for Iranian vessel interdiction of commercial ships; US escort authority; repeat interdiction escalates to Tier 3 |
| Annex Pa (Patrol Boat Protocol) | Articles 4, 5 | IRGC-Navy patrol zone definitions; permitted interception criteria; hotline escalation for patrol encounters |
| Annex PC (Political Stability Hold) | Articles 2, 9 | 60-90 day political stability hold for elections or leadership transitions; core obligations continue during hold period |
| Annex Q (IRGC Compliance) | Article 8 | IRGC-specific compliance framework; IRGC-Iran government coordination; independent IRGC reporting obligations |
| Annex R / R.a (Escalation Buffer) | Articles 1, 12 | 72-hour mandatory cooling-off for incidents; Tier 1-3 escalation ladder; guarantor state emergency consultations |
| Annex S (Reciprocal Sequencing) | Articles 7, 11 | 60-day reciprocal sanctions relief sequencing; escrow release milestones; asset tranche schedule |
| Annex T (Step-Back/Earn-Back) | Articles 7, 12 | Compliance enforcement: three-tier graduated response; earn-back path; good-faith exception; quiet periods |
| Annex U (Technical Demarcation) | Articles 1, 13 | Digital Registry for territory-specific and actor-specific commitments; shared factual baseline |
| Annex V (Nuclear Dust Protocol) | Article 8 | Emergency HEU dispersal contingency; HEU container breach response; environmental monitoring |
| Annex V.S (Verification Sequencing) | Article 8 | IAEA verification schedule; dual-lock custody verification chain; mass spectrometry sampling protocols |
| Annex W (Maritime Telemetry) | Articles 4, 5 | Dual-Key Transit system: 24-hour telemetry standard for breakout-relevant facilities; Swiss-hosted Dashboard; automated anomaly detection |
| Annex X (Mutual Standstill) | Articles 1, 2 | US-Israel coordination: no Israeli military action against Iranian nuclear/maritime targets while Framework active; Tel Aviv Channel |
| Annex Y (Dual-Key Custody) | Article 8 | HEU dual-lock architecture: IAEA holds monitoring keys, Iran holds physical keys, US holds verification keys; material accountancy; custody chain documentation |
| Annex Ya (Irreversible Disposition) | Article 8 | Module for pathways that are physically irreversible (e.g., Pathway W — Agriculture/Food Security); no reversal after point of no return |
| Annex Y.b (Pathway Operational Sequencing) | Article 8 | Detailed technical procedures for each of the 11 disposition pathways; batch splitting provision; cross-pathway coordination |
| Annex Z (Transformation Pathways) | Article 8 | In-Iran disposition options menu: civilian nuclear products (Pathway N), industrial uranium products (Pathway O), depleted uranium industrial (Pathway T), agriculture and food security (Pathway W) |

# Part 4: Consolidated Timeline (Day 1 to Day 730)

This timeline integrates all MOU articles, framework provisions, and annex references into a single chronological action sequence from Day 1 through Day 730.

| Day | MOU Ref | Action | Responsible Party | Annex Reference |
| --- | --- | --- | --- | --- |
| Day 1 | Arts 1, 4, 5, 10 | Ceasefire enters force on all fronts; blockade lift begins; OFAC oil/petrochemical waivers issued; $5B mutual escrow deposited; HEU freeze declared; IAEA consolidation begins; JHA stands up; JCC operational | US + Iran + Oman + IAEA | Annex Mi, Annex N, PSF Art 1.1, Art 6 |
| Day 3 | Arts 4, 5 | First humanitarian vessel transits Hormuz; 72-hour mine-free certification | JHA MCC + Oman | Annex Mi Section 2 |
| Day 7 | Arts 4, 5 | Synchronized blockade lift complete; Hormuz open to commercial traffic; $2.5B first escrow tranche releases; IAEA stand-off posture confirmed | US 5th Fleet + IRGC Navy + Oman | Annex Mi Phase 3, PSF Art 6.3 |
| Day 14 | Art 8 | IAEA baseline inventory complete; dual-key custody fully established | IAEA + AEOI + US Technical Agent | Annex Y, Annex V.S |
| Day 15 | Art 11 | Second escrow tranche ($2.5B) releases if continued compliance confirmed | Swiss Escrow Facilitator | Annex C / HSC Annex C |
| Day 30 | Arts 4, 5, 7, 11 | Hormuz at pre-war transit volume; first sanctions relief tranche (15%); first frozen asset tranche ($3.6B); $1B Joint Disposition Fund operational | US Treasury + Iran + Swiss | Annex S, Annex 7.1, PSF Art 1.5-A |
| Day 45 | Arts 7, 11 | SWIFT Phase 1 (5-bank pilot); second asset tranche (30% cumulative); second sanctions tranche | US Treasury + OFAC + Central Bank Iran | Annex S, PSF Art 9 |
| Day 60 | Arts 3, 7, 8, 11 | Final agreement deadline; or extension; Phase II entry certificate or deadlock procedures activate | All Parties + PCC | Annex D, MOU of PEACE Art 11 |
| Day 90 | Art 14 | UNSC resolution target adoption (recommended, not in frameworks) | Joint US-Iran diplomatic mission | NOT IN FRAMEWORKS — GAP |
| Day 150 | Art 3 | Deadlock resolution deadline if Phase II not entered by Day 60 | PCC + Guarantor Matrix | Annex D Phase 3 |
| Day 180 | Arts 7, 8, 11 | Pathway A (in-Iran downblending) auto-activates if no disposition pathway selected; 45% sanctions relief; 45% frozen assets released | PCC + JIG + IAEA | PSF Art 1.6, Annex Z |
| Day 365 | Arts 8, 9 | Phase I Rolling Horizon auto-renewal point; Iran may request IAEA custody termination (with 180 days notice); 65% cumulative relief | All Parties + IAEA | PSF Art 17, Art 1.6-B |
| Day 540 | Art 8 | Phase II nuclear negotiating window closes (if entered at Day 60) | All Parties | PSF Art 1.5 |
| Day 730 | Art 8 | Pathway W (Agriculture and Food Security) auto-activates if no pathway selected; 100% cumulative relief and asset release | PCC + IAEA | PSF Art 1.6-B, Annex Ya |

## Rolling Horizon Architecture

The Provisional Steps Framework v1.8 (Article 17) replaces fixed-term traps with a Rolling Horizon: every 180 days, both executives must actively confirm continuation. Non-response after 45 days = automatic termination after orderly exit period. Termination requires 30 days written notice, capped exit payment ($10B), and HEU return to Iran under IAEA supervision.

# Part 5: Crisis Response Matrix

This fire-drill guide addresses the 10 most likely crisis scenarios, ranked by probability. Each row identifies the affected MOU articles, annexes to activate, immediate actions, timelines, and escalation paths. Designed for sub-60-second reference during active crises.

| Crisis Scenario | MOU Art. | Annexes | Immediate Action | Timeline | Escalation Path |
| --- | --- | --- | --- | --- | --- |
| 1. Israeli strike on Iranian nuclear facility | Arts 1, 2, 8 | Annex R.c (Regional Standstill) + Annex X (Mutual Standstill) + Annex E (US Assurance) | 72-hour mandatory cooling-off; Tel Aviv Channel activated; guarantor states notified | Hours 0-72 | PCC emergency session within 4 hrs; Guarantor Matrix convenes; Tier 3 if strike confirmed unprovoked; Iran may suspend reciprocal obligations proportionally |
| 2. IRGC denies IAEA inspector access | Art 8 | Annex O (IAEA Access) + Annex Q (IRGC Compliance) | NAC (National Access Coordinator) must override within 24 hours; IAEA files formal access report | 24-72 hours | Tier 2 escalation if unresolved; automatic sanctions relief suspension (Art 3.6); expedited PCA arbitration within 7 days |
| 3. HEU telemetry fails for 48+ hours | Art 8 | Annex 3.6 (Auto-Suspension) + Annex Y (Dual-Key) | ALL sanctions relief automatically suspended — no human veto permitted; IAEA dispatches emergency inspection team | Immediate | Relief restoration only upon IAEA certification that telemetry restored and authentic; Tier 2 step-back if tampering confirmed |
| 4. Iranian vessel interdicts commercial ship | Arts 4, 5 | Annex N.a (Backdoor Closure) + Annex Pa (Patrol Boat Protocol) | Automatic $1M/day penalty assessed against escrow; US escort authority activates; incident logged on Dashboard | Immediate-72 hrs | Tier 2 on first incident; Tier 3 on repeat interdiction within 30 days; full blockade review |
| 5. Hezbollah cross-border attack into Israel | Arts 1, 6 | Annex K (Lebanon Firewall) + Annex J (Lebanon Linkage) | 72-hour diplomatic consultation via Lebanon Firewall architecture; PCC impairment determination; Band 3 Differential Processing activates | 72 hours | Tier 2 step-back ONLY if PCC finds Iran complicity by clear-and-convincing evidence; nuclear/maritime cores continue unaffected |
| 6. Lebanon ceasefire collapses | Art 1 | Annex K (Lebanon Firewall) + Annex U (Technical Demarcation) | FIREWALL: Nuclear and maritime cores continue unaffected; Regional Stabilization Round convened; Digital Registry updated | 24-72 hrs | Phase I benefits continue for Iran; Lebanon-only exit available (Art 6.9); re-entry requires 90-day trial period |
| 7. US reimposes sanctions unilaterally | Arts 7, 11 | Annex E (US Assurance) + Annex T (Step-Back) | Iran may file expedited PCA arbitration within 96 hours; escrow funds protected by humanitarian firewall | 96 hours | PCA ruling within 5-7 days; Iran may suspend reciprocal obligations proportionally; full earn-back available upon reversal |
| 8. Deadlock on final agreement at Day 60 | Art 3 | Annex D (Phase II Deadlock Mechanism) | 90-day cooling-off period; ministerial consultation; binding PCA arbitration if deadlock persists | Days 60-150 | Phase I benefits continue; Extended Phase I activates if arbitration fails; Day 180 pathway default still applies |
| 9. Iran selects no disposition pathway by Day 180 | Art 8 | Annex 1.6 + Annex Z (Pathway A default) | Pathway A (in-Iran downblending to medical-grade LEU at Esfahan) activates automatically; IAEA verifies commencement within 7 days | Day 180 | No penalties; no US veto; all relief continues; Iran may still select alternative pathway through Day 365; Day 730 Pathway W ultimate backstop |
| 10. Internal regime change in Iran or US election | Arts 2, 12 | Annex IC (Institutional Continuity) + Annex PC (Political Stability Hold) | 60-90 day Political Stability Hold; core obligations continue; new administration review period | 60-90 days | Withdrawal requires 30 days notice + capped $10B exit payment; HEU returned to Iran under IAEA supervision; successor government bound for 5 years |

## Crisis Response Quick Reference

- Tier 1 (Minor): Diplomatic note; 72-hour cooling-off; technical team consultation. No automatic penalties.

- Tier 2 (Material): Specific sanctions relief tranche suspended; escrow hold; enhanced monitoring. Reversible through Tier 2 Earn-Back.

- Tier 3 (Deliberate Hostile): Full step-back; all discretionary relief suspended; Guarantor Matrix emergency session; 30-day ultimatum before Framework collapse.

- Emergency Contact Test: Daily at 06:00 UTC. Failure to answer = Tier 1 dispute. Three consecutive failures = Tier 2.

# Part 6: Key Contacts Directory

The following roles are designated across the frameworks. Primary and secondary contacts are placeholders pending formal nomination by each party. All contacts must be certified and tested before Framework activation (PSF Article 28).

| Role | Entity | Annex Ref | Primary | Secondary |
| --- | --- | --- | --- | --- |
| PCC Co-Chair (US) | United States | MOU of PEACE Art 9 | [Secretary of State / Designee] | [Deputy Secretary / Designee] |
| PCC Co-Chair (Iran) | Iran | MOU of PEACE Art 9 | [Foreign Minister / Designee] | [Deputy Foreign Minister / Designee] |
| National Access Coordinator (NAC) | Iran (AEOI) | Annex Q Art 3 | [AEOI Deputy Director / Designee] | [AEOI Technical Director / Designee] |
| IAEA Senior IDM Inspector | IAEA | Annex Ya Art 2 | [IAEA Director of Safeguards / Designee] | [IAEA Iran Desk Chief / Designee] |
| JHA Maritime Coordination Cell Director | Oman | Annex W Art 1 | [Omani Navy Commander / Designee] | [Omani Coast Guard Chief / Designee] |
| US Technical Agent (Dual-Key) | United States | Annex Y Art 1.2 | [NNSA Administrator / Designee] | [DOE National Labs Director / Designee] |
| Swiss Escrow Facilitator | Switzerland | Annex Y Art 8.3 | [Swiss State Secretariat for Economic Affairs / Designee] | [Swiss National Bank / Designee] |
| JMC Convenor (rotating) | US / Iran (90-day) | Annex Mo Art 1.2 | [Rotating — US or Iran nominee] | [Rotating alternate] |
| JMC Deputy Convenor | Pakistan | Annex Mo Art 1.3 | [Pakistani Foreign Secretary / Designee] | [Pakistani DG MOFA / Designee] |
| Tel Aviv Channel Designated Official | US + Israel | Annex X Art 1 | [US Ambassador to Israel / Designee] | [Israeli National Security Advisor / Designee] |
| Joint Disposition Fund Administrator | Swiss + IAEA | PSF Art 1.5-A | [Swiss Development Agency / Designee] | [IAEA Technical Cooperation / Designee] |
| Lebanon Firewall Coordinator | UNIFIL + PCC | Annex K Sec 12.4 | [UNIFIL Force Commander / Designee] | [PCC Lebanon Desk Officer / Designee] |
| Crisis Communications Director | Swiss | PSF Art 28 | [Swiss FDFA Spokesperson / Designee] | [Swiss Embassy Tehran / Designee] |

# Part 7: Implementation Checklist

This checklist breaks implementation into three phases with specific actions, responsible parties, and annex references. Use for tracking operational readiness and Day-1 execution.

## Phase 1: Day 1-7 (Immediate Execution)

| Status | Action | Responsible | Annex Reference |
| --- | --- | --- | --- |
| ☐ | Ceasefire enters force on all fronts (Lebanon, Gaza, Syria, Yemen) | US + Iran + Allies | MOU Art 1 |
| ☐ | HEU stockpile declared frozen; IAEA begins 14-day consolidation | Iran (AEOI) + IAEA | Annex Y, PSF Art 1.1 |
| ☐ | $5B mutual escrow deposited in Zurich | US + Iran + Swiss | Annex C, PSF Art 8 |
| ☐ | US Treasury issues OFAC general license for Iranian oil/petrochemical exports | US Treasury | MOU Art 10, PSF Art 1.4 |
| ☐ | US naval forces transition to stand-off posture (5nm from Hormuz corridor) | US 5th Fleet | PSF Art 1.4, Art 6 |
| ☐ | Iran begins mine clearance in Hormuz transit corridor | IRGC Navy + Oman | Annex Mi |
| ☐ | Joint Hormuz Authority (JHA) stands up; MCC operational | Oman + US + Iran | Annex W, PSF Art 4 |
| ☐ | JCC stands up; crisis contacts designated and tested | PCC + All Parties | Annex Mo, PSF Art 25 |
| ☐ | Centrifuge production ban enters force; mothball protocol activates | Iran (AEOI) | PSF Art 2.3, Art 3 |
| ☐ | Black-Box telemetry sensors activated at breakout-relevant facilities | IAEA + Iran | PSF Art 3.3, Art 3.5 |
| ☐ | Daily crisis communication test at 06:00 UTC initiated | All Parties | PSF Art 28 |

## Phase 2: Day 8-30 (Consolidation)

| Status | Action | Responsible | Annex Reference |
| --- | --- | --- | --- |
| ☐ | Synchronized blockade lift complete (Day 7 trigger) | US 5th Fleet + IRGC Navy | Annex Mi Phase 3 |
| ☐ | Hormuz at pre-war transit volume | JHA MCC | MOU Art 5 |
| ☐ | IAEA baseline inventory complete; mass spectrometry confirms isotopic composition | IAEA | Annex V.S |
| ☐ | Dual-key custody fully established (Pathway A default unless Iran selects alternative) | IAEA + US Technical Agent + Iran | Annex Y |
| ☐ | First escrow tranche ($2.5B) released on Day 7 milestone | Swiss Escrow Facilitator | Annex C |
| ☐ | First sanctions relief tranche (15%) on IAEA certification | US Treasury + OFAC | Annex S, Annex 7.1 |
| ☐ | First frozen asset tranche ($3.6B / 15%) released | Swiss + Central Bank Iran | HSC Annex C |
| ☐ | OFAC general license extended for humanitarian trade (90 days) | US Treasury | PSF Art 1.4 |
| ☐ | JHTA 12-month pilot phase launched | JHA Council | PSF Art 4 |
| ☐ | PCC holds first quarterly meeting | PCC Co-Chairs | MOU of PEACE Art 9 |

## Phase 3: Day 31-60 (Negotiation Window)

| Status | Action | Responsible | Annex Reference |
| --- | --- | --- | --- |
| ☐ | SWIFT Phase 1: 5-bank pilot reconnection | US Treasury + OFAC + Central Bank Iran | PSF Art 9 |
| ☐ | Second escrow tranche ($2.5B) on continued compliance | Swiss Escrow Facilitator | Annex C |
| ☐ | Joint Disposition Fund ($1B) operational; first drawdown available | Swiss + IAEA | PSF Art 1.5-A |
| ☐ | Iran selects preferred disposition pathway (preferred choice, not binding) | Iran (AEOI) + JIG | PSF Art 1.5 |
| ☐ | Final agreement negotiations enter Phase II (if deadlock not triggered) | All Parties | MOU Art 3, Annex D |
| ☐ | UNSC resolution track: informal P5 consultations (recommended parallel track) | Joint diplomatic mission | MOU Art 14 — GAP |
| ☐ | $300B Rehabilitation Fund: Phase III negotiation track initiated (recommended) | PCC + IFIs | MOU Art 6 — GAP |

## Post-Day 60: Long-Range Triggers

| Milestone | Action | Responsible | Reference |
| --- | --- | --- | --- |
| Day 90 | UNSC resolution target adoption | Joint diplomatic mission | MOU Art 14 — GAP |
| Day 150 | Deadlock resolution deadline (if triggered) | PCC + Guarantor Matrix | Annex D |
| Day 180 | Pathway A auto-activation if no pathway selected | IAEA + JIG | PSF Art 1.6 |
| Day 365 | Rolling Horizon renewal point; Iran may request custody termination | All Parties + IAEA | PSF Art 17, Art 1.6-B |
| Day 730 | Pathway W irreversible default | IAEA + PCC | PSF Art 1.6-B, Annex Ya |

## Gap Status Summary

Two MOU articles are not fully operationalized in existing frameworks:

- Article 6 ($300B Rehabilitation Fund): Recommend Phase III negotiation track with IFI involvement. Current frameworks provide ~$11B maximum operational funding.

- Article 14 (UNSC Resolution): Recommend standalone diplomatic track modeled on UNSCR 2231. Begin informal P5 consultations on Day 1.

Implementation Matrix

MOU to Framework Mapping

Version 1.0  |  June 2026

Confidential — Authorized Negotiators Only

"Trust is good. Verification is better. But a Framework that survives without either — that is architecture."